## Feature List
Serial | Feature Name | Time (hrs) | Cost (per hr) | Total
Tour Operator Features (Operator Dashboard)
1 | Tour operator segmentation and account data model | 16 | 50
2 | Tour operator authentication and onboarding workflow with email verification and guided setup | 24 | 50
3 | Tour operator dashboard: application shell, role-aware navigation and KPI overview | 40 | 50
4 | Tour creation workflow: multi-step wizard integrated with the admin review pipeline | 40 | 50
5 | Operator verification and approval workflow with a pending / verified / rejected status lifecycle | 24 | 50
6 | Tour listing management: media, localized descriptions, pricing, inclusions and exclusions, meeting points and add-ons | 80 | 50
7 | Per-tour availability configuration: recurring schedules and date-level exceptions | 40 | 50
8 | Commission tier selection per tour with eligibility gating, plus Destination Spotlight request submission | 24 | 50
9 | Booking management for owned tours: balance payment links and traveller non-payment reporting | 40 | 50
10 | Earnings, settlement and payout history reporting | 24 | 50
11 | Operator team management: staff seats with scoped, limited permissions | 24 | 50
12 | iCal calendar synchronization: tokenized, rotatable and revocable bookings and departures feeds (.ics) | 24 | 50
13 | Calendar management: month view with per-departure occupancy, close/reopen controls for days and slots, and manual departure creation | 40 | 50
14 | Availability management: departure inventory, capacity adjustments, sold-out marking and reopen controls | 40 | 50
15 | Operator-scoped booking listings with filtering and detail views | 16 | 50
16 | Cancellation request queue within the operator dashboard | 16 | 50
17 | Operator-scoped customer directory with per-customer booking statistics | 24 | 50
18 | Operator payment and settlement history views with ledger-derived statuses | 16 | 50
19 | Tour submission tracking: review status, moderator notes and change history | 24 | 50
20 | Operator notification inbox and transactional email pipeline | 24 | 50
21 | Operator media gallery: upload, organization and asset reuse | 32 | 50
22 | In-dashboard translation management for operator-authored content | 32 | 50
23 | Commercial tier administration: 30-day tier lock and derived deposit percentage | 24 | 50
24 | Tier-based ranking engine with a nightly demand-signal job assigning the "Likely to sell out" badge | 40 | 50
25 | Weekly recurring schedule configuration with per-schedule start times | 24 | 50
26 | Daily capacity limits and per-booking traveller limit enforcement | 16 | 50
27 | Bulk blackout-date management and a one-tap "close today" control | 16 | 50
28 | Publish-readiness validation panel: requirement checklist gating publication | 24 | 50
29 | Per-tour payment model selection (operator link / on arrival / paid in full) | 16 | 50
30 | Automated operator email notifications on booking confirmation | 16 | 50
31 | Manual translation overrides across the six non-English locales | 24 | 50
32 | Advanced pricing engine: per-person age-band pricing versus whole-unit / private charter pricing, with extra-guest surcharge and day/overnight charter handling | 56 | 50
33 | Live-edit gate for published tours: staged revisions, field-level diffs, review round-trip and post-rejection revival | 64 | 50
34 | Operator conditions module: per-tour terms document authoring enforced through a checkout acknowledgment gate | 32 | 50
35 | Global availability calendar with a cross-tour daily agenda: month/week/day views, close-all-today and data-freshness confirmation | 48 | 50
36 | Operator business settings: company profile, social links, payout provider selection and payment configuration | 16 | 50
37 | Operator profile and account security management (avatar, password) | 16 | 50
38 | Dashboard command palette (Cmd+K) with role-scoped entity search and quick actions | 16 | 50
Subtotal: Tour Operator Features (Operator Dashboard)
Admin (Island Tours) Features (Admin Dashboard)
39 | Destination management with seeded-row deletion protection and region grouping | 40 | 50
40 | Global 19-category taxonomy management | 32 | 50
41 | Activity hub management with editorial content blocks and comparison tables | 48 | 50
42 | Curated collection management with manual ordering and dynamic query modes | 40 | 50
43 | Editorial content and FAQ block management across all public page types | 32 | 50
44 | Destination Spotlight request adjudication: approve or reject, capped at three per destination | 16 | 50
45 | Editorial flag curation, including "Locals' Favourite", with coverage tracking | 16 | 50
46 | Homepage hero and destination feature curation | 24 | 50
47 | Review moderation: approve, hold or reject, bulk actions and operator response management | 24 | 50
48 | Cancellation handling and refund processing queue with refund-entitlement computation | 32 | 50
49 | Operator non-payment confirmation workflow: deposit forfeiture and capacity release | 16 | 50
50 | Force-majeure exemption management for island-wide date ranges | 16 | 50
51 | Operator onboarding administration and tour submission status review | 32 | 50
52 | Platform staff account administration | 24 | 50
53 | Global platform settings configuration | 24 | 50
54 | Payment gateway configuration and credential management (Stripe and Mollie, admin-switchable) | 24 | 50
55 | Provider-backed live currency conversion at checkout | 24 | 50
56 | Category administration: per-category page content and SEO metadata management | 24 | 50
57 | Dashboard analytics: sales, revenue and refund metrics, trend graphs and an activity feed | 48 | 50
58 | Locals' favourites curation and post-booking recommendation engine administration (thank-you page and email placements) | 40 | 50
59 | Tour attribute dictionary: definition management and per-tour value assignment | 24 | 50
60 | Email activity tracking and administration of the transactional and operator email engine | 48 | 50
61 | Pages CMS: permalink-based page creation with rich text and server-side HTML sanitization | 40 | 50
62 | Global site settings and configuration management | 16 | 50
63 | Site-wide SEO administration and server-side tracking configuration | 24 | 50
64 | AI translation administration with provider-agnostic model routing across eight switchable providers | 48 | 50
65 | Cookie consent integration and management (Consent Mode v2) | 16 | 50
66 | Instagram feed integration administration: connection, sync scheduling, curation and layout control | 40 | 50
67 | Platform review aggregation with a switchable provider (Trustpilot / Google) | 24 | 50
68 | Transactional and scheduled marketing email administration | 32 | 50
69 | Custom script injection engine: admin-managed vendor snippets rendered on public pages | 24 | 50
70 | Global operations calendar spanning all operators' departures, bookings, schedules and exceptions | 40 | 50
71 | Customer administration with bulk email and one-click review request dispatch | 24 | 50
72 | Operator payout and settlement administration: mark-as-paid with confirmation and undo | 32 | 50
73 | Full tour lifecycle administration, including availability and exceptions, within the tour wizard | 48 | 50
74 | Submission moderation queue: change requests and publication of newly submitted tours (FIFO lane) | 32 | 50
75 | Content-change moderation queue for live tours with field-level diff review | 40 | 50
76 | Multi-model payment orchestration: deposit via operator link, on arrival, paid in full and operator-collected | 40 | 50
77 | Tour badge administration (Sponsored, Most Popular, Likely to Sell Out, New) with precedence rules | 16 | 50
78 | Unified administration of page content, FAQs, translations and localization | 40 | 50
79 | Search dropdown and popular-link curation administration | 16 | 50
80 | Role and permission administration: RBAC and PBAC with ~140 deny-by-default permissions | 56 | 50
81 | Tour search and filter engine: relevance ranking, tier-aware ordering and typeahead suggestions | 48 | 50
82 | Platform-wide financial reporting: gross booking value, commission and refunds | 32 | 50
83 | Booking outcome analytics: commit rates, funnel and payment-mix breakdowns | 24 | 50
84 | Centralized media library: signed uploads, bulk operations and shared pickers for images and video | 40 | 50
85 | Site-wide translation workspace: seven-locale coverage matrix with per-field AI translation | 48 | 50
86 | WhatsApp support integration with a dashboard-managed number and deep links across site and email surfaces | 8 | 50
Subtotal: Admin (Island Tours) Features (Admin Dashboard)
Staff & Teams Features
87 | Role-based dashboard access with predefined permission sets | 16 | 50
88 | Catalog curation and editorial operations under assigned rights | 16 | 50
89 | Review moderation and customer support operations | 16 | 50
90 | Read access to operator tour listings and operational readiness statuses | 8 | 50
91 | Cancellation request processing within permitted scope | 8 | 50
92 | Designation-scoped visibility into operator and platform metrics | 8 | 50
93 | Unified Staff & Teams engine: a single seat model for platform staff and operator teams, reusable designation templates, and effective-permission computation with grant ceilings and permission floors | 64 | 50
94 | Seat lifecycle management: email invitations, acceptance, activation and suspension with immediate session revocation | 32 | 50
95 | Dedicated staff login surface with enumeration-proof sign-in, forgot-password and reset flows | 16 | 50
Subtotal: Staff & Teams Features
Traveller / Customer Account Features
96 | Traveller account area: booking and payment listings with summary statistics | 32 | 50
97 | Booking tracking page: design and dynamic implementation | 24 | 50
98 | Self-service cancellation flow with refund-outcome state handling | 24 | 50
99 | Tokenized marketing email unsubscribe page | 8 | 50
100 | Review submission page accessed through signed, secured links | 16 | 50
101 | Traveller login page: design and dynamic implementation | 16 | 50
102 | Automatic traveller account provisioning on first booking, with welcome / set-password email | 24 | 50
103 | Booking-reference lookup authentication (email + reference) with lost-reference recovery and rate limiting | 24 | 50
104 | Booking session security: signed session tokens, masked thank-you rendering and enumeration-proof lookups | 32 | 50
105 | Traveller profile management and printable payment receipts | 16 | 50
106 | Self-service date-change engine: atomic seat swap within the free-cancellation window | 32 | 50
107 | Add-to-calendar (ICS) export and confirmation resend from booking pages | 8 | 50
Subtotal: Traveller / Customer Account Features
Public Website (Frontend) Features
108 | Slug registry integration for frontend routing and rendering: automatic 301 redirects and a 90-day slug reuse cooldown | 40 | 50
109 | Public wishlist functionality: optimistic heart toggles backed by a list API | 16 | 50
110 | Public site design system and page foundation: design tokens, typography scale, responsive layouts and motion standards | 64 | 50
111 | Homepage: design and dynamic implementation (hero island search, trust strip, top experiences, testimonials, editorial banner, FAQs) | 40 | 50
112 | Destination page: design and dynamic implementation (locals' favourites, collections, category quick links, editorial copy, FAQs, Instagram strip) | 40 | 50
113 | All-tours listing page: design and dynamic implementation (filterable, sortable, paginated per-destination catalog) | 40 | 50
114 | Category page: design and dynamic implementation (ranked grid, editorial content, three-tour visibility gating) | 32 | 50
115 | Activity hub page: design and dynamic implementation (fast facts, curated picks, comparison table, local tips, related hubs) | 56 | 50
116 | Collection page: design and dynamic implementation (curated grids, rationale copy, numbered and persona list styles) | 32 | 50
117 | Tour detail page: design and dynamic implementation (gallery, content sections, meeting and pickup logic, reviews, related tours, structured data) | 72 | 50
118 | Checkout page: design and dynamic implementation (contact, pickup, special requests, persistent summary, inline validation) | 64 | 50
119 | Thank-you page: design and dynamic implementation (payment-model-aware confirmation, next steps, cross-sell, conversion event) | 32 | 50
120 | Search results page: design and dynamic implementation | 24 | 50
121 | Wishlist page: design and dynamic implementation | 16 | 50
122 | Error and 404 pages: design and implementation | 8 | 50
123 | Server-side tracking, SEO metadata, structured JSON-LD and sitemap generation | 48 | 50
124 | Parallel and intercepting routes for operator condition documents: in-flow modal plus a persistent canonical URL | 16 | 50
125 | Legal page suite: six CMS-backed pages plus cookie preference management | 16 | 50
126 | Dynamic booking widget: live availability calendar, time slots, party and age-band selection, add-ons and server-authoritative quotes across seven locales | 96 | 50
127 | Payment method interface: inline card element plus PayPal and iDEAL redirects, a collapsed method list and a processing page with settle-on-return | 40 | 50
128 | Global navigation and footer system: island selector, category dropdown, search entry, language and currency switchers, mobile menu | 32 | 50
129 | Site-wide search typeahead with grouped suggestions and a curated zero-state panel | 24 | 50
130 | Standard tour card component: photo carousel, badge system and wishlist heart, shared across all listing surfaces | 32 | 50
131 | Faceted filtering and sorting system: filter modal, URL-persisted state, applied chips, pagination and dual result counts | 40 | 50
132 | Tour page review presentation: rating summary, star distribution, filtering and machine-translated reviews with a show-original toggle | 32 | 50
133 | Seven-locale public site delivery with per-field English fallback and locale-prefixed routing | 56 | 50
134 | Multi-currency display layer: geolocation-detected defaults, footer switcher and live re-pricing of mounted pages | 32 | 50
135 | Rendering architecture: partial prerendering, cached data loaders with tag-based invalidation, streaming skeletons and a cross-application cache revalidation bridge | 48 | 50
Subtotal: Public Website (Frontend) Features
Backend Platform & Core Engines
136 | Booking engine: server-side quotes, reserve/confirm/cancel lifecycle, hold expiry, overbooking-proof atomic seat claims, immutable snapshots and instant confirmation | 96 | 50
137 | Availability engine: weekly schedules and exceptions materialized into a rolling 12-month departure inventory, with nightly refresh and bookability recomputation | 80 | 50
138 | Server-authoritative pricing and quote engine: tamper-proof totals, deposit and balance splits, add-ons and pickup zones | 48 | 50
139 | Commission tier engine: five tiers, a 30-day change lock, commission snapshotting and deposit-percentage derivation | 32 | 50
140 | Eligibility engine: 90-day provisional window, nightly evaluation, notification, grace period and automatic demotion | 40 | 50
141 | Nightly quality-score computation and a canonical ranking query with a diversity pass | 32 | 50
142 | Destination Spotlight lifecycle: request, approval, active window and expiry, with a 35% commission overlay and max-3 enforcement | 24 | 50
143 | Settlement ledger engine: per-booking money position, post-cancellation-window payout eligibility and reversal self-healing | 40 | 50
144 | FX and multi-currency engine: immutable rate history, ECB rate provider, booking-time snapshots and PSP charge-rate reconciliation | 40 | 50
145 | Stripe payment processing: payment intents, signature-verified idempotent webhooks and refund execution with retry | 48 | 50
146 | Mollie payment provider: switchable PSP with hosted checkout, webhook reconciliation and provider-routed refunds | 32 | 50
147 | Cancellation engine: unified free-cancellation window, refund verdict computation, seat release and forfeiture workflow | 32 | 50
148 | Authentication platform: session engine, ordered guard chain, brute-force limits and four isolated login surfaces | 56 | 50
149 | Background job platform: queue infrastructure, scheduled jobs, a transactional outbox and the nightly commercial pipeline | 40 | 50
150 | OCTO-standard distribution API: supplier, tour and availability endpoints with capability negotiation and HMAC-signed webhooks | 56 | 50
151 | Review platform backend: booking-gated submission, moderation lifecycle, rating aggregates and the invitation loop | 48 | 50
152 | Media pipeline: Cloudinary signed uploads, asynchronous processing, metadata extraction and transformation policy | 32 | 50
Subtotal: Backend Platform & Core Engines
Emails & Notifications
153 | Booking confirmation email: wireframe-exact templating across seven locales and four payment models, with calendar attachment | 40 | 50
154 | Cancellation email suite: traveller acknowledgment, operator notice, admin work item and refund-verdict-aware confirmations | 24 | 50
155 | Pre-tour reminder email dispatched 24 hours before departure in island-local time, with logistics and cross-sell content | 16 | 50
156 | Review invitation and reminder emails with administrator-configured scheduling and a suppression matrix | 16 | 50
157 | Post-trip marketing email with consent capture and one-click unsubscribe | 16 | 50
158 | Operator onboarding email sequence: a nine-email drip with send windows and suppression rules | 40 | 50
159 | Account and authentication email set: welcome, invitations, password reset, verification and email change (dark-mode-safe templates) | 16 | 50
160 | Email delivery spine: exactly-once send log, suppression records, per-entity timelines and administrative resend | 32 | 50
161 | In-application notification inbox: bell feed, sidebar badges, login digest and permission-gated audience fan-out | 40 | 50
Subtotal: Emails & Notifications
Infrastructure, Deployment & Quality
162 | Production VPS deployment: containerized stack, reverse proxy with TLS, PostgreSQL/Redis and a migrate-on-boot entrypoint | 32 | 50
163 | CI/CD pipelines: automated build, test and deployment for the backend, with auto-deploy for both frontends | 24 | 50
164 | Environment validation and a layered secrets model with rotation procedures | 8 | 50
165 | Automated test coverage: 1,600+ backend assertions, including concurrency and overbooking scenarios, plus end-to-end suites | 80 | 50
166 | Seed tooling: first-boot production bootstrap seed and a re-runnable demo dataset | 24 | 50
167 | Dashboard extraction into an independently deployable application with parity verification | 64 | 50
168 | Dashboard design system: token architecture, dark mode, unified data tables, status badges and lint-enforced rules | 48 | 50
Subtotal: Infrastructure, Deployment & Quality
GRAND TOTAL